## Risk Assessment
Risk ID | Assessment Date | Business Unit | Location | Compliance Area | Requirement / Regulation | Risk Description | Risk Owner | Likelihood (1-5) | Impact (1-5) | Inherent Risk Score | Existing Controls | Control Effectiveness (%) | Residual Risk Score | Risk Rating | Remediation Required? | Action Plan | Target Date | Status | Estimated Remediation Cost | Actual Remediation Cost | Days to Target | Overdue Flag | Evidence / Notes
RA-001 | 2026-01-15 | IT Security | New York, NY | Information Security | SOC 2 / Internal Access Policy | Quarterly user access reviews not completed for privileged accounts | James Carter | 4 | 5 |  | Role-based access control; annual access attestation | 45% |  |  |  | Implement automated quarterly access review workflow and revoke stale accounts | 2026-04-30 | In Progress | 18000 | 9500 |  |  | Access review report Q1 2026; IAM tool export
RA-002 | 2026-02-06 | Marketing | Los Angeles, CA | Privacy | CCPA / State Privacy Laws | Consumer data retained beyond documented retention schedule | Emily Brooks | 3 | 4 |  | Data retention policy; manual deletion requests | 60% |  |  |  | Deploy automated retention enforcement and update privacy notices | 2026-06-15 | Closed | 12500 | 11800 |  |  | Retention schedule v3; deletion log March 2026
RA-003 | 2026-02-27 | Human Resources | Chicago, IL | Employment | USCIS Form I-9 / IRCA | Missing or incomplete I-9 documentation for recent hires | Michael Turner | 4 | 4 |  | HR onboarding checklist; annual I-9 audit | 35% |  |  |  | Conduct full I-9 self-audit and remediate deficiencies within 60 days | 2026-05-31 | In Progress | 8500 | 4200 |  |  | HRIS audit sample; corrective action tracker
RA-004 | 2026-03-13 | Operations | Houston, TX | OSHA | OSHA 29 CFR 1910 Training Requirements | Incomplete workplace safety training records for warehouse staff | Ashley Morgan | 3 | 5 |  | LMS tracking; supervisor spot checks | 55% |  |  |  | Reconcile LMS records, schedule make-up training, update tracking | 2026-04-15 | Closed | 5200 | 4900 |  |  | LMS completion report; sign-in sheets
RA-005 | 2026-04-03 | Finance | Dallas, TX | Financial Reporting | SOX 404 / Internal Approval Matrix | Journal entries posted without required secondary approval | David Wilson | 4 | 5 |  | ERP approval workflow; monthly review | 40% |  |  |  | Enforce mandatory dual-approval workflow in ERP for all manual entries | 2026-08-31 | Open | 28000 | 0 |  |  | ERP exception report; JE sampling memo
RA-006 | 2026-04-24 | Payroll | Phoenix, AZ | Payroll | IRS W-2 / 1099 Reporting / FICA | Discrepancies between payroll register and W-2 / 1099 filings | Jessica Reed | 3 | 4 |  | Quarterly reconciliation; third-party payroll provider review | 65% |  |  |  | Perform year-to-date reconciliation and file corrected forms if needed | 2026-07-31 | In Progress | 6800 | 2100 |  |  | Q1 2026 reconciliation workbook
RA-007 | 2026-05-15 | Procurement | Seattle, WA | Vendor Management | Vendor Risk Policy / PCI DSS 12.8 | Third-party vendors onboarded without completed due diligence | Chris Bennett | 3 | 3 |  | Vendor intake form; contract review | 50% |  |  |  | Retroactive due diligence on active vendors; block onboarding without review | 2026-09-30 | Open | 9500 | 0 |  |  | Vendor inventory list; intake form stats
RA-008 | 2026-06-05 | Human Resources | Philadelphia, PA | Records Retention | Records Retention Policy / State Law | Inactive employee files retained past disposal date | Sarah Mitchell | 2 | 3 |  | Retention schedule; annual records purge | 70% |  |  |  | Schedule certified destruction of expired files and update inventory | 2026-08-15 | Open | 2800 | 0 |  |  | Records inventory; destruction vendor quote
RA-009 | 2026-07-24 | IT Security | Austin, TX | Information Security | Incident Response Plan / SOC 2 CC7 | Incident response plan not tested in over 12 months | Robert Hayes | 2 | 4 |  | Documented IR plan; escalation contacts | 30% |  |  |  | Run tabletop exercise and update IR plan with lessons learned | 2026-10-31 | Open | 1500 | 0 |  |  | Last tabletop report dated 2025; IR plan v2
Formulas:
Days to Target = IFERROR([Target Date]-TODAY(),"")
Overdue Flag = IF(AND([Target Date]<TODAY(),[Status]<>"Closed"),"Overdue","On Track")

## Dashboard
Compliance Risk Dashboard — 2026
Total Assessments |  | Open Risks |  | Critical / High Risks
Average Residual Risk |  | Total Estimated Cost |  | Total Actual Cost
Risks by Rating |  | Risks by Compliance Area
Risk Rating | Count | Compliance Area | Count | Avg Residual | Est. Cost | Actual Cost
Critical |  | Privacy
High |  | Employment
Medium |  | OSHA
Low |  | Financial Reporting
Records Retention
Information Security
Payroll
Vendor Management
Risk Lookup (enter Risk ID)
RA-001
Risk Owner
Regulation
Risk Rating
Status
Target Date

## Instructions
Compliance Risk Assessment Template — Instructions
Overview
This workbook helps US organizations identify, score, and track compliance risks, assign owners, manage remediation actions, and summarize overall risk exposure.
Risk Assessment Sheet
Enter one risk per row. Yellow cells are editable input fields; navy-tinted formula cells calculate automatically.
Scoring
Score Likelihood and Impact from 1 (lowest) to 5 (highest). Inherent Risk = Likelihood x Impact. Residual Risk = Inherent Risk adjusted by Control Effectiveness.
Requirements
Document the applicable laws, regulations, internal policies, or contractual requirements for each risk.
Controls
Describe existing controls and estimate Control Effectiveness as a percentage (0% to 100%).
Ownership & Dates
Assign a responsible Risk Owner and a realistic Target Date for every remediation action.
US References
Use US frameworks where applicable: OSHA, IRS, HIPAA, PCI DSS, SOC 2, FICA/payroll requirements, W-2/W-9/1099 documentation, and state privacy laws such as CCPA.
Monitoring
Review the Dashboard regularly. Focus first on Critical/High ratings and any item flagged as Overdue.
Status Values
Use Open, In Progress, Closed, or Accepted. Closed items no longer count as open risks.
Data Privacy
Do NOT enter actual SSNs, passwords, confidential medical information, or other sensitive personal data in this workbook.