## Daily Log
Construction Site Daily Diary — Riverside Office Tower Project
Project Manager: Michael Turner ¦ Site Address: 480 Harbor Ave, Seattle, WA ¦ Reporting Period: July 2026
Date | Weather | Temp (F) | Crew Size | Hours Worked | Total Labor Hrs | Equipment On Site | Work Performed | Delay Hours | Delay Status | Safety Incidents | Visitors | Site Supervisor | Hourly Rate | Labor Cost | Notes | Supervisor | Hourly Rate
07/06/2026 | Sunny | 78 | 12 | 8 |  | Excavator, Crane | Foundation pouring - Section A | 0 |  | 1 | 3 | James Wilson |  |  |  | James Wilson | 42.5
07/07/2026 | Cloudy | 72 | 14 | 8 |  | Crane, Concrete Mixer | Rebar installation - Level 1 | 0.5 |  | 0 | 2 | James Wilson |  |  |  | Sarah Johnson | 45
07/08/2026 | Rainy | 65 | 10 | 6 |  | Concrete Mixer | Delayed pour due to rain | 2 |  | 0 | 5 | Sarah Johnson |  |  |  | David Ramirez | 40
07/09/2026 | Sunny | 80 | 15 | 9 |  | Crane, Forklift | Steel framing - Level 1 | 0 |  | 0 | 1 | James Wilson |  |  |  | Emily Carter | 43.75
07/10/2026 | Windy | 74 | 13 | 8 |  | Crane, Forklift | Steel framing - Level 2 | 0 |  | 1 | 4 | Sarah Johnson
07/13/2026 | Sunny | 82 | 16 | 9 |  | Crane, Excavator | Electrical rough-in - Level 1 | 0 |  | 0 | 0 | David Ramirez
07/14/2026 | Foggy | 68 | 11 | 7 |  | Forklift, Generator | Plumbing rough-in - Level 1 | 1 |  | 0 | 2 | David Ramirez
07/15/2026 | Sunny | 79 | 14 | 8 |  | Crane, Concrete Mixer | Concrete pour - Level 2 slab | 0 |  | 0 | 6 | Sarah Johnson
07/16/2026 | Cloudy | 71 | 12 | 8 |  | Forklift, Scaffolding | Masonry work - exterior wall | 0 |  | 0 | 3 | James Wilson
07/17/2026 | Sunny | 77 | 15 | 8 |  | Crane, Forklift | HVAC ductwork installation | 0 |  | 1 | 5 | David Ramirez
TOTALS / AVERAGES

## Dashboard
Site Diary Dashboard — Riverside Office Tower Project
KEY PERFORMANCE INDICATORS | WEATHER DISTRIBUTION
Total Labor Hours | Sunny
Total Delay Hours | Cloudy
Total Safety Incidents | Rainy
Total Visitors | Windy
Average Temp (F) | Foggy
Total Labor Cost | Snowy

## Instructions
How to Use This Construction Site Diary Template
Section | Description
Daily Log sheet | Enter one row per working day. Fields with a pale-yellow background (Weather, Crew Size, Hours Worked, Delay Hours, Safety Incidents, Visitors, Site Supervisor) are meant to be edited daily.
Weather / Supervisor dropdowns | Click the cell to choose a value from the dropdown list instead of typing free text, to keep data consistent.
Total Labor Hrs (col F) | Automatically calculated as Crew Size x Hours Worked. Do not overwrite this formula.
Delay Status (col J) | Automatically flags a day as 'Delayed' whenever Delay Hours (col I) is greater than zero.
Hourly Rate / Labor Cost (col N, O) | Hourly Rate is looked up automatically from the Supervisor Rate table (columns R:S) based on the Site Supervisor selected. Labor Cost = Total Labor Hrs x Hourly Rate.
Totals row | The amber row at the bottom of the Daily Log automatically sums or averages each column across all logged days.
Dashboard sheet | Shows key performance indicators (total hours, delays, incidents, visitors, average temperature, total labor cost) plus a bar chart of daily labor hours, a line chart of the temperature trend, and a pie chart of weather distribution.
Adding more days | Insert new rows above the Totals row in the Daily Log sheet and copy the formulas from column F, J, N, and O down into the new rows.
Conditional formatting | Any day with Delay Hours or Safety Incidents greater than zero is automatically highlighted in red so issues are easy to spot.