## Decision Log
Decision ID | Decision Date | Decision Title | Business Area | Decision Owner | Stakeholders | Decision Type | Decision Status | Priority | Options Considered | Selected Option | Rationale | Expected Impact ($) | Implementation Cost ($) | Target Date | Actual Completion Date | Outcome Rating | Review Date | Days Open | Overdue Flag | Notes
DEC-2026-001 | 2026-01-08 | CRM Migration Vendor Selection | IT | James Carter (New York) | Sales Team; IT Staff; Finance | Strategic | Implemented | High | Salesforce; HubSpot; Microsoft Dynamics 365 | Microsoft Dynamics 365 | Best integration with the existing ERP and lowest three-year total cost of ownership. | 185000 | 92000 | 2026-04-15 | 2026-04-02 | 5 | 2026-07-15 |  |  | Migration completed two weeks early with zero downtime.
DEC-2026-002 | 2026-02-03 | Digital Advertising Budget Approval | Marketing | Emily Johnson (Los Angeles) | Marketing Team; CFO; Creative Agency | Financial | Approved | High | Increase budget 20%; Maintain current spend; Reduce budget 10% | Increase budget 20% | Paid channels delivered a 3.2x return on ad spend in the prior year. | 120000 | 85000 | 2026-03-31 |  |  | 2026-09-30 |  |  | Funds released for Q2-Q3 campaigns.
DEC-2026-003 | 2026-02-20 | Warehouse Shipping Provider Selection | Operations | Michael Davis (Chicago) | Logistics Team; Procurement; Warehouse Staff | Operational | Implemented | Medium | FedEx; UPS; Regional carrier consortium | UPS | Lower bulk-shipment rates and a stronger on-time delivery service-level agreement. | 64000 | 12500 | 2026-05-01 | 2026-04-28 | 4 | 2026-08-01 |  |  | New rates effective for all outbound freight.
DEC-2026-004 | 2026-03-05 | Office Relocation to Downtown Houston | Operations | Ashley Martinez (Houston) | Facilities; HR; Finance; Department Heads | Strategic | Deferred | Medium | Relocate in Q3 2026; Renew current lease; Sublease excess space | Renew current lease | Renewal avoids business disruption during the ongoing ERP rollout. | 48000 | 95000 | 2026-09-30 |  |  | 2026-10-15 |  |  | Revisit relocation after ERP go-live.
DEC-2026-005 | 2026-03-18 | Cybersecurity Awareness Program | IT | David Wilson (Phoenix) | IT Security; All Employees; Compliance Officer | Compliance | Implemented | High | In-house training; External vendor workshops; E-learning platform | E-learning platform | Scalable, trackable completion reporting and the lowest cost per employee. | 78000 | 34000 | 2026-05-30 | 2026-05-22 | 5 | 2026-11-30 |  |  | 98% employee completion in the first month.
DEC-2026-006 | 2026-04-02 | Health Plan Renewal Option | HR | Jessica Brown (Philadelphia) | Benefits Committee; CFO; Insurance Broker | Financial | Approved | High | Renew current plan; Switch carrier; Add HSA option | Add HSA option | Reduces premiums by 8% while expanding employee choice. | 96000 | 22000 | 2026-06-15 |  |  | 2026-12-01 |  |  | Enrollment materials delayed by the broker.
DEC-2026-007 | 2026-04-24 | Customer Support Software Upgrade | Product | Chris Anderson (San Antonio) | Support Team; IT; Customer Success | Operational | Implemented | Medium | Upgrade existing tier; Migrate to Zendesk; Build in-house tool | Migrate to Zendesk | Better automation and reporting at a similar annual cost. | 54000 | 28000 | 2026-06-01 | 2026-06-05 | 4 | 2026-09-01 |  |  | Average ticket resolution time down 22%.
DEC-2026-008 | 2026-05-14 | Proposed AI Chatbot Feature | Product | Sarah Thomas (Dallas) | Product Team; Engineering; Sales Leadership | Strategic | Rejected | Low | Build chatbot in-house; Partner with vendor; Defer to 2027 | Defer to 2027 | Engineering capacity is fully committed to the core product roadmap. | 40000 | 65000 | 2026-08-31 |  |  | 2026-10-31 |  |  | Re-evaluate during 2027 planning cycle.
DEC-2026-009 | 2026-06-26 | Hybrid-Work Policy Update | HR | Robert Taylor (Austin) | Executive Team; All Staff; Legal Counsel | Compliance | Proposed | Medium | Three days in office; Two days in office; Fully remote | Two days in office | Balances collaboration needs with employee retention goals. | 33000 | 15000 | 2026-10-01 |  |  | 2026-11-15 |  |  | Pending executive committee sign-off.
Formulas:
Days Open = IF([Decision Status]="Implemented",IF([Actual Completion Date]="",TODAY()-[Decision Date],[Actual Completion Date]-[Decision Date]),TODAY()-[Decision Date])
Overdue Flag = IF(AND([Decision Status]<>"Implemented",TODAY()>[Target Date]),"Overdue","On Track")

## Dashboard
Decision Log Dashboard - Management Summary 2026
Key Performance Indicators
| Total Decisions | Approved Decisions | Implemented Decisions | Overdue Decisions
| Average Outcome Rating | Total Expected Impact | Implementation Cost | Implementation Rate
| Decision Status Summary |  |  | Expected Impact by Business Area |  | Decisions by Priority
| Status | Count |  | Business Area | Expected Impact | Priority | Count
| Proposed |  |  | Marketing |  | High
| Approved |  |  | Finance |  | Medium
| Implemented |  |  | Operations |  | Low
| Deferred |  |  | Product
| Rejected |  |  | HR
IT
Selected Decision Lookup
| Enter Decision ID: | DEC-2026-003

## Instructions
Decision Log Template - Instructions
How to Use This Workbook
1 | Enter one decision per row on the Decision Log sheet. Assign a sequential Decision ID such as DEC-2026-010.
2 | Use the dropdown lists for Business Area, Decision Type, Decision Status, Priority, and Outcome Rating to keep categories standardized. Dropdown cells are shaded pale yellow.
3 | Complete the Options Considered, Selected Option, Rationale, Expected Impact ($), Implementation Cost ($), and Target Date columns for every decision.
4 | Review overdue decisions weekly. The Days Open and Overdue Flag columns calculate automatically; overdue items are highlighted in red.
5 | Update the Decision Status and Actual Completion Date when work is finished, then enter an Outcome Rating from 1 to 5.
6 | Use the Dashboard sheet for management reporting and decision follow-up. Enter a Decision ID in the Selected Decision Lookup area to retrieve its title instantly.
Column Guide
Column | Description
Decision ID | Unique sequential identifier, e.g. DEC-2026-001.
Days Open | Automatic: days since the decision date, or days to completion once Implemented.
Overdue Flag | Automatic: shows Overdue when the target date has passed and the decision is not Implemented.
Outcome Rating | Rate implemented decisions from 1 (poor) to 5 (excellent).
Review Date | Next scheduled date to revisit the decision outcome.
Note: All dollar amounts are in USD. All dates use the US MM/DD/YYYY format. Sample data dates are set in 2026.