## Wedding_Plan
Indian Wedding Planner - Project Timeline & Budget
Event Phase | Task | Category | Assigned To | Due Date | Status | Priority | Estimated Cost | Actual Cost | Variance | Paid? | Notes | Completion Helper
Pre-Wedding | Venue booking - Grand Ballroom | Venue | Priya Sharma | 01/15/2026 | Completed | High | 15000 | 15500 |  |  | Deposit secured
Pre-Wedding | Caterer selection - Edison, NJ | Catering | Raj Patel | 02/01/2026 | Completed | High | 8000 | 7800 |  |  | Tasting done
Pre-Wedding | Photographer booking - Chicago | Photography | Neha Gupta | 02/10/2026 | In Progress | Medium | 4500 | 0 |  |  | Awaiting contract
Pre-Wedding | Mehendi artist - Los Angeles | Beauty | Anjali Rao | 03/05/2026 | Pending | Medium | 1200 | 0 |  |  | Shortlisted 2 artists
Wedding Day | DJ/live music - Houston | Entertainment | Vikram Singh | 04/12/2026 | In Progress | High | 3000 | 3200 |  |  | Sound check pending
Wedding Day | Florals/decor - Dallas | Decor | Sonal Mehta | 04/15/2026 | Pending | High | 6000 | 0 |  |  | Mandap design review
Pre-Wedding | Invitations - San Jose | Invitations | Kiran Desai | 01/25/2026 | Completed | Low | 800 | 750 |  |  | Digital + printed sets
Pre-Wedding | Bridal wear fitting - Phoenix | Attire | Priya Sharma | 03/20/2026 | In Progress | High | 5000 | 5400 |  |  | Second fitting scheduled
Wedding Day | Transportation - Philadelphia | Logistics | Amit Joshi | 04/18/2026 | Pending | Medium | 1500 | 0 |  |  | Baraat vehicles TBD
Wedding Day | Priest/ceremony arrangements - Austin | Ceremonies | Pandit Sharma | 04/20/2026 | Completed | High | 1000 | 1000 |  |  | Sankalp items confirmed
Budget Summary
Total Estimated Cost
Total Actual Cost
Total Variance
Completion Rate

## Budget_Summary
Wedding Budget Summary Dashboard
Category | Planned Budget | Actual Spend | Difference | Spend % | Status
Venue | 15000 | 15500
Catering | 8000 | 7800
Decor | 6000 | 5600
Photography | 4500 | 4300
Entertainment | 3000 | 3200
Attire | 5000 | 5400
Invitations | 800 | 750
Transportation | 1500 | 1400
Ceremonies | 1000 | 1000
Miscellaneous | 2000 | 2300
TOTAL

## Vendors
Vendor Contact & Selection Tracker
Vendor Type | Vendor Name | Contact Person | City | Phone | Email | Quote Amount | Deposit Paid | Balance Due | Contract Status | Rating | Notes
Venue | The Grand Ballroom NYC | Sarah Williams | New York | 212-555-0110 | info@grandballroomnyc.com | 15000 | 5000 |  | Booked | 5 | Excellent hall for 400 guests
Caterer | Edison Spice Kitchen | Raj Malhotra | Edison | 732-555-0142 | events@edisonspice.com | 8000 | 3000 |  | Booked | 4 | Multi-cuisine Indian menu
Photographer | Chicago Frame Studio | David Chen | Chicago | 312-555-0187 | hello@chicagoframe.com | 4500 | 1000 |  | Quoted | 4 | Candid + traditional package
Mehendi Artist | Anjali Henna Art | Anjali Rao | Los Angeles | 213-555-0199 | anjali@hennaart.com | 1200 | 0 |  | Pending | 5 | Bridal + guest packages
Makeup Artist | Glow by Meera | Meera Iyer | Los Angeles | 213-555-0176 | meera@glowbeauty.com | 1800 | 500 |  | Booked | 5 | HD makeup specialist
Florist | Dallas Bloom Decor | Sonal Mehta | Dallas | 214-555-0123 | sonal@dallasbloom.com | 6000 | 2000 |  | Quoted | 4 | Mandap floral design
DJ | Houston Beats Entertainment | Vikram Singh | Houston | 713-555-0165 | vikram@houstonbeats.com | 3000 | 1000 |  | Booked | 4 | Bollywood + fusion sets
Transportation | Philly Elite Rides | Amit Joshi | Philadelphia | 215-555-0134 | amit@phillyelite.com | 1500 | 0 |  | Pending | 3 | Baraat vehicles + shuttle
Priest/Officiant | Pandit Ashok Sharma | Ashok Sharma | Austin | 512-555-0198 | pandit.sharma@ceremonies.com | 1000 | 500 |  | Booked | 5 | Traditional Hindu ceremony
Videographer | San Jose Cinematics | Kevin Park | San Jose | 408-555-0121 | kevin@sjcinematics.com | 3500 | 0 |  | Quoted | 4 | Cinematic highlight reel
Vendor Metrics
Average Rating
Vendors Booked
Vendors Pending

## Instructions
Indian Wedding Planner - User Guide
Sheet Overview
Wedding_Plan | Track every task by event phase (Pre-Wedding, Wedding Day, Post-Wedding), assign owners, set due dates, and monitor estimated vs actual cost. Variance and Paid? columns update automatically.
Budget_Summary | A dashboard rollup of planned vs actual spend by category, with charts comparing budget vs actual and a donut chart showing allocation share.
Vendors | Vendor contact tracker with quote amounts, deposits, balance due, contract status, and ratings for each vendor category.
How to Update Task Statuses and Costs
Status column | Use the dropdown in the Status column (Pending, In Progress, Completed, On Hold) on the Wedding_Plan sheet to reflect current progress.
Cost columns | Enter Estimated Cost and Actual Cost as numbers only. Variance and Paid? flags will calculate automatically - do not overwrite these formula cells.
How to Enter Vendor Quotes and Deposits
Quote Amount / Deposit Paid | Enter the vendor quote and any deposit paid on the Vendors sheet. Balance Due calculates automatically as Quote Amount minus Deposit Paid.
Contract Status | Use the dropdown (Pending, Quoted, Booked, Cancelled) to track vendor booking progress.
Where Formulas Should Not Be Overwritten
Protected formula cells | Do not type over cells in the Variance, Paid?, Difference, Spend %, Status, Balance Due, or summary total cells - these are calculated automatically from your inputs.
Color Meanings
Yellow cells | Pale yellow (#FFFBEB) marks editable input cells such as Estimated Cost, Actual Cost, Planned Budget, Actual Spend, Quote Amount, and Deposit Paid.
Green text | Green (#16A34A) indicates positive results - under budget, savings, or booked vendors.
Red text | Red (#DC2626) flags alerts - over budget items, pending vendor contracts, or unpaid balances.
Amber rows | Amber (#F4A62A) highlights key summary totals and KPI tiles.
Formatting Notes
Date format | All dates use MM/DD/YYYY format (US standard), for example 04/20/2026.
Currency format | All monetary values use US currency format, for example $1,234.56.