## Risk Register
ISO 9001:2015 Risk Assessment & Treatment Register
Risk ID | Risk Category | Risk Description | Related Process/Clause | Likelihood (1-5) | Severity (1-5) | Risk Score | Risk Level | Existing Controls | Mitigation Action | Risk Owner | Target Date | Status | Residual Likelihood | Residual Severity | Residual Score | Residual Level | Risk Reduction %
R-001 | Supplier Management | Late or non-conforming raw material deliveries from key supplier | Purchasing (8.4) | 4 | 4 |  |  | Supplier scorecards, incoming inspection | Qualify second-source supplier; tighten SLA | David Martinez | 09/15/2026 | Open | 2 | 3
R-002 | Process Control | Machine calibration drift causing out-of-spec production | Production (8.5) | 3 | 5 |  |  | Preventive maintenance schedule | Increase calibration frequency; add SPC checks | Sarah Johnson | 08/30/2026 | In Progress | 2 | 3
R-003 | Document Control | Obsolete work instructions used on shop floor | Document Control (7.5) | 3 | 3 |  |  | Document control software with version tracking | Automated obsolete-doc removal alerts | Emily Chen | 08/10/2026 | Open | 1 | 2
R-004 | Customer Satisfaction | Rising customer complaints on product packaging defects | Customer Focus (9.1.2) | 4 | 3 |  |  | Complaint log, monthly review | Root cause analysis with packaging vendor | Michael Brown | 09/01/2026 | In Progress | 2 | 2
R-005 | Equipment/Calibration | Measurement equipment used past calibration due date | Monitoring & Measuring (7.1.5) | 2 | 4 |  |  | Calibration tracking spreadsheet | Implement automated calibration reminders | Chris Anderson | 08/20/2026 | Open | 1 | 3
R-006 | Human Resources | Loss of competency due to key employee turnover | Competence (7.2) | 3 | 4 |  |  | Cross-training program | Formal succession plan and documented SOPs | Ashley Davis | 10/05/2026 | Not Started | 2 | 3
R-007 | Internal Audit | Recurring nonconformances not effectively closed | Internal Audit (9.2) | 3 | 3 |  |  | CAPA tracking log | Root cause training for auditors | James Wilson | 09/25/2026 | In Progress | 1 | 2
R-008 | Information Security | Unauthorized access to quality records database | Info. Security (7.5.3) | 2 | 5 |  |  | Password policy, restricted user roles | Implement multi-factor authentication | Jessica Taylor | 08/15/2026 | Open | 1 | 4
R-009 | Change Management | Engineering changes implemented without impact review | Change Control (6.3) | 4 | 4 |  |  | Change request form | Mandatory change impact assessment sign-off | David Martinez | 09/10/2026 | Not Started | 2 | 3
R-010 | Inventory Management | Expired/obsolete materials used in production | Resources (7.1) | 2 | 3 |  |  | FIFO labeling system | Barcode expiration scanning at point of use | Sarah Johnson | 10/15/2026 | Open | 1 | 2
SUMMARY |  | Total Risks | Average Risk Score | High/Critical Risks | Average Residual Score | Avg Risk Reduction %

## Risk Matrix
ISO 9001 Risk Scoring Matrix & Reference Scales
Risk Score Lookup Table (sorted ascending - used by VLOOKUP)
Score (Min) | Risk Level | Priority Action | Color Code
1 | Low | Monitor periodically; no immediate action required | Green
5 | Medium | Assign owner; treat within normal review cycle | Yellow
10 | High | Prioritize mitigation; management review required | Orange
16 | Critical | Immediate action; escalate to top management | Red
Note: VLOOKUP uses approximate match (TRUE) - a score falls into the highest bracket whose Min value is <= the score.
Likelihood Scale (1-5) |  |  | Severity Scale (1-5)
Rating | Description |  | Rating | Description
1 | Rare - may occur only in exceptional circumstances |  | 1 | Negligible - minimal impact on quality objectives
2 | Unlikely - could occur at some time |  | 2 | Minor - limited impact, easily corrected
3 | Possible - might occur at some time |  | 3 | Moderate - noticeable impact on process/customer
4 | Likely - will probably occur in most circumstances |  | 4 | Major - significant impact on compliance or customer
5 | Almost Certain - expected to occur in most circumstances |  | 5 | Catastrophic - certification, safety, or legal impact

## Dashboard
Quality Risk Assessment Dashboard
Total Risks | Open/In Progress | High + Critical | Avg Risk Score | Avg Risk Reduction
Risk Count by Category |  |  | Risk Level Distribution
Category | Count |  | Level | Count
Supplier Management |  |  | Low
Process Control |  |  | Medium
Document Control |  |  | High
Customer Satisfaction |  |  | Critical
Equipment/Calibration
Human Resources
Internal Audit
Information Security
Change Management
Inventory Management

## Instructions
How to Use This ISO 9001 Risk Assessment Template
Overview | This workbook helps quality managers identify, assess, treat, and monitor risks and opportunities per ISO 9001:2015 clause 6.1. It contains four sheets: Risk Register, Risk Matrix, Dashboard, and Instructions.
Risk Register Sheet | Enter each identified risk with a unique ID, category, description, and related process/clause. Rate Likelihood and Severity from 1 (lowest) to 5 (highest) - the Risk Score and Risk Level are calculated automatically using the lookup table on the Risk Matrix sheet.
Mitigation & Residual Risk | Document existing controls and planned mitigation actions, assign an owner and target date, and track status via the dropdown. After controls are implemented, re-rate the Residual Likelihood and Severity to see the Residual Score, Residual Level, and % Risk Reduction achieved.
Risk Matrix Sheet | Contains the reference lookup table (Score to Risk Level) plus the Likelihood and Severity rating scales. Do not delete or reorder this table - the VLOOKUP formulas in the Risk Register depend on it remaining sorted ascending by Score (Min).
Dashboard Sheet | Shows key metrics (total risks, open items, high/critical risks, average score, average risk reduction) plus a bar chart of risks by category and a pie chart of risk level distribution, updated automatically from the Risk Register.
Data Entry Tips | Cells shaded pale yellow are meant for manual input. Use the dropdown lists provided for Risk Category and Status to keep data consistent. Likelihood and Severity fields are restricted to whole numbers between 1 and 5.
Best Practices | Review and update this register at least quarterly or after any significant process change, audit finding, or customer complaint, as required by your Quality Management System's risk-based thinking approach.