## Task List
Master Task List Tracker
ID | Task Name | Category | Assigned To | Priority | Status | Start Date | Due Date | Progress % | Days Remaining | Overdue Flag | Est. Hours | Notes
1 | Prepare Q3 budget report | Finance | James Carter | High | In Progress | 07/01/2026 | 07/20/2026 | 60 |  |  | 8
2 | Update client contact list | Admin | Emily Turner | Medium | Not Started | 07/05/2026 | 07/25/2026 | 0 |  |  | 6
3 | Design new landing page | Marketing | Michael Reyes | High | In Progress | 06/28/2026 | 07/18/2026 | 75 |  |  | 10
4 | Schedule team offsite | HR | Ashley Brooks | Low | Completed | 06/15/2026 | 07/01/2026 | 100 |  |  | 4
5 | Fix checkout page bug | Engineering | David Kim | High | In Progress | 07/08/2026 | 07/17/2026 | 40 |  |  | 12
6 | Review vendor contracts | Legal | Jessica Lopez | Medium | Not Started | 07/10/2026 | 08/01/2026 | 0 |  |  | 5
7 | Onboard new sales rep | HR | Chris Anderson | Medium | In Progress | 07/02/2026 | 07/22/2026 | 50 |  |  | 8
8 | Prepare investor presentation | Finance | Sarah Mitchell | High | Not Started | 07/14/2026 | 07/30/2026 | 10 |  |  | 15
9 | Audit inventory records | Operations | James Carter | Low | Completed | 06/20/2026 | 07/05/2026 | 100 |  |  | 6
10 | Plan Q4 marketing campaign | Marketing | Emily Turner | Medium | In Progress | 07/12/2026 | 08/05/2026 | 25 |  |  | 20
Totals / Averages
Quick Task Lookup
Enter Task ID: | 1
Task Name:
Assigned To:
Status:
Formulas:
Days Remaining = IFERROR([Due Date]-TODAY(),"")
Overdue Flag = IF(AND([Status]<>"Completed",[Due Date]<TODAY()),"Overdue","On Track")

## Dashboard
Task List Dashboard
Metric | Value
Total Tasks
Completed Tasks
In Progress Tasks
Not Started Tasks
Overdue Tasks
High Priority Tasks
Average Progress %
Total Estimated Hours
Status | Count
Not Started
In Progress
Completed
Category | Task Count
Finance
Admin
Marketing
HR
Engineering
Legal
Operations

## Instructions
How to Use This Template
Section | Description
Task List sheet | The main worksheet where you record every task. Fill in Task Name, Category, Assigned To, Priority, Status, Start Date, Due Date, Progress %, Est. Hours, and Notes. Yellow-filled cells are meant to be edited by you.
Category / Priority / Status | Use the dropdown lists provided in these columns to keep entries consistent. Click any cell in these columns to see the available options.
Days Remaining | Automatically calculated as Due Date minus today's date using the TODAY() function. Updates every time the file is opened.
Overdue Flag | Automatically flags a task as 'Overdue' if it is not marked Completed and its due date has already passed. Overdue rows are highlighted in red.
Totals / Averages row | Shows the average progress percentage and total estimated hours across all tasks.
Quick Task Lookup | Type a Task ID number in the yellow cell to instantly retrieve that task's name, assignee, and status using the VLOOKUP function.
Dashboard sheet | Provides key metrics (total, completed, in-progress, overdue, and high-priority task counts) plus a pie chart of status distribution and a bar chart of tasks by category.
Conditional formatting | High priority tasks, completed tasks, and overdue tasks are automatically color-coded so you can scan the list quickly.
Customizing | Feel free to add more rows to the Task List sheet. Just copy the formulas from the last row (Days Remaining, Overdue Flag) into your new rows and extend the dropdown ranges if needed.