## Marketing Timeline
MARKETING CAMPAIGN TIMELINE — 2026
Campaign ID | Campaign Name | Marketing Channel | Campaign Owner | Target Market | Start Date | End Date | Status | Priority | Budget | Actual Spend | Leads | Conversions | Completion % | Duration (Days) | Budget Variance | Cost per Lead | Expected CPL | Performance Flag | Notes
CMP-001 | Spring Product Launch | Email | Emily | New York | 2026-02-02 | 2026-03-31 | Complete | High | 24000 | 23500 | 1450 | 203
CMP-002 | Paid Search Refresh | Paid Search | James | Chicago | 2026-03-09 | 2026-05-15 | Complete | Medium | 36000 | 37200 | 980 | 118
CMP-003 | Summer Social Campaign | Social Media | Ashley | Los Angeles | 2026-06-01 | 2026-08-14 | In Progress | High | 28000 | 17500 | 720 | 79
CMP-004 | Small Business Webinar | Events | Michael | Austin | 2026-04-20 | 2026-05-08 | Complete | Low | 9500 | 9100 | 210 | 34
CMP-005 | Back-to-School Promotion | Email | Jessica | Dallas | 2026-07-27 | 2026-09-11 | In Progress | High | 18500 | 8200 | 640 | 96
CMP-006 | Local Retail Partnership | Partnerships | David | Houston | 2026-05-04 | 2026-10-30 | On Hold | Medium | 22000 | 6800 | 190 | 21
CMP-007 | Fall Content Series | Content | Sarah | Seattle | 2026-09-01 | 2026-11-13 | Planned | Medium | 14000 | 0 | 0 | 0
CMP-008 | Holiday Preview Campaign | Display Ads | Robert | Philadelphia | 2026-10-05 | 2026-11-20 | Planned | High | 31000 | 0 | 0 | 0
CMP-009 | Customer Referral Drive | Referral | Amanda | San Antonio | 2026-08-03 | 2026-10-16 | In Progress | Medium | 12000 | 5400 | 310 | 58
TOTALS

## Dashboard
MARKETING PERFORMANCE DASHBOARD — 2026
KEY PERFORMANCE INDICATORS |  |  |  |  | CHANNEL BENCHMARKS
Total Campaigns |  |  |  |  | Marketing Channel | Expected CPL
Active Campaigns |  |  |  |  | Email | 18
Total Budget |  |  |  |  | Paid Search | 42
Actual Spend |  |  |  |  | Social Media | 28
Total Leads |  |  |  |  | Events | 65
Total Conversions |  |  |  |  | Partnerships | 35
Average Completion Rate |  |  |  |  | Content | 30
Overall Conversion Rate |  |  |  |  | Display Ads | 48
Campaigns Needing Review |  |  |  |  | Referral | 22
Budget vs Actual Spend by Campaign
Campaign | Budget | Actual Spend | Start Date | End Date
Campaigns by Status
Status | Count
Planned
In Progress
Complete
On Hold

## Instructions
HOW TO USE THE MARKETING TIMELINE TEMPLATE
GETTING STARTED
1 | Enter or update campaign details in the yellow input cells on the Marketing Timeline sheet (columns A–M and Notes).
2 | Enter all dates in MM/DD/YYYY format (US standard). Start Date must be on or before End Date.
3 | Use the dropdown lists for Marketing Channel, Status, and Priority to keep entries consistent.
4 | Calculated columns (Completion %, Duration, Budget Variance, Cost per Lead, Expected CPL, Performance Flag) fill in automatically — do not overwrite them.
5 | Update the Channel Benchmarks table (Expected CPL) on the Dashboard whenever your planning assumptions change.
6 | Use the Dashboard KPIs and charts to monitor campaign timing, spending, leads, and conversions at a glance.
COLOR LEGEND
Pale yellow — editable input cell
Green — positive result / On Track performance
Red — alert: Review flag or negative Budget Variance
Amber — totals and section highlights
SHEET GUIDE
Marketing Timeline | Master campaign plan: schedule, budget, spend, leads, conversions, and automatic performance calculations.
Dashboard | Executive KPIs, channel CPL benchmarks, and charts for spend, timeline, and status mix.
Instructions | This guide and the color legend.