## Project Status Tracker
Multiple Project Status Report - Project Status Tracker
Project ID | Project Name | Client/Department | Project Manager | Start Date | Due Date | % Complete | Priority | Status | Budget ($) | Actual Spend ($) | Variance ($) | Days Remaining | On Track? | Notes
PRJ-001 | Marketing Campaign Redesign | Marketing Dept (New York) | James Carter | 2026-01-15 | 2026-03-15 | 100 | High | Complete | 45000 | 43500 |  |  |  | Delivered ahead of budget
PRJ-002 | Website Refresh | IT Department (Los Angeles) | Emily Nguyen | 2026-02-01 | 2026-05-30 | 65 | Medium | In Progress | 62000 | 39000 |  |  |  | On schedule, dev phase
PRJ-003 | CRM Migration | Sales Dept (Chicago) | Michael Thompson | 2026-01-10 | 2026-08-15 | 40 | Critical | At Risk | 125000 | 98000 |  |  |  | Vendor delays reported
PRJ-004 | Product Launch Prep | Product Team (Houston) | Ashley Martinez | 2026-03-01 | 2026-06-01 | 55 | High | In Progress | 85000 | 91000 |  |  |  | Over budget, needs review
PRJ-005 | Client Onboarding Automation | Customer Success (Phoenix) | David Wilson | 2026-05-01 | 2026-09-30 | 0 | Medium | Not Started | 38000 | 2000 |  |  |  | Kickoff scheduled
PRJ-006 | Quarterly Sales Dashboard | Finance Dept (Philadelphia) | Jessica Brown | 2026-01-05 | 2026-02-28 | 100 | Low | Complete | 15000 | 14200 |  |  |  | Closed under budget
PRJ-007 | Office Relocation Planning | Operations (Dallas) | Chris Taylor | 2026-02-15 | 2026-12-01 | 30 | Critical | At Risk | 95000 | 102000 |  |  |  | Lease negotiation pending
PRJ-008 | Training Program Rollout | HR Department (Austin) | Sarah Johnson | 2026-03-10 | 2026-06-30 | 75 | Medium | In Progress | 27000 | 20000 |  |  |  | Module 3 in progress
PRJ-009 | Vendor Contract Review | Procurement (Seattle) | Robert Lee | 2026-01-20 | 2026-03-01 | 100 | Low | Complete | 8500 | 8100 |  |  |  | Contracts finalized
Formulas:
Days Remaining = [Due Date]-TODAY()

## Dashboard Summary
Executive Dashboard - Project Portfolio Summary
Total Projects |  | Completed Projects |  | In Progress Projects | Overdue Projects
Average % Complete |  | Total Budget |  | Total Actual Spend | Total Variance
Status | Count |  | Priority | Budget Share | Project | % Complete
Not Started |  |  | Low
In Progress |  |  | Medium
At Risk |  |  | High
Complete |  |  | Critical
On Hold

## Status Code Legend & Instructions
Status Code Legend & Instructions
Status Code | Meaning | Suggested Fill Color
Not Started | Project has not begun yet | Gray
In Progress | Project is actively underway | Light Blue
At Risk | Project may miss deadline or budget | Yellow/Amber
Complete | Project has been finished | Green
On Hold | Project is paused temporarily | Light Gray
Priority Levels
Low | Minimal urgency, flexible timeline
Medium | Standard priority, monitor regularly
High | Requires close attention and resources
Critical | Immediate action required, top priority
Instructions
- Enter project data only in the pale yellow input cells on the Project Status Tracker sheet.
- Use the dropdown lists provided for the Status and Priority columns to keep entries consistent.
- Review the Dashboard Summary sheet regularly for overdue items and budget variance alerts.
- All dates must be entered in MM/DD/YYYY format.
- Variance, Days Remaining, and On Track columns are calculated automatically - do not overwrite them.
- Green variance values indicate the project is under budget; red values indicate an overspend.
- The On Track column shows 'No' when a project is overdue, over 100% incomplete deadline, or already complete but still flagged.