## Non-Conformance Log
NCR ID | Date Reported | Department | Reported By | Location | Source Type | Product/Process | Description of Non-Conformance | Requirement/Standard | Severity | Quantity Affected | Estimated Cost Impact | Immediate Containment Action | Root Cause Category | Corrective Action | Preventive Action | Responsible Owner | Target Due Date | Actual Closure Date | Status | Days Open | Overdue Flag | Verification Result | Final Disposition | Notes
NCR-2026-001 | 2026-01-15 | Supply Chain | James Miller | Chicago | Supplier | Aluminum Housing Assembly | Incoming aluminum housings have visible surface scratches beyond acceptance limits. | QP-104 Incoming Material Acceptance Criteria | Major | 120 | 4800 | Quarantined affected lot and notified supplier. | Supplier | Issue supplier corrective action request and inspect replacement lot. | Add cosmetic defect trend review to supplier scorecard. | Michael Davis | 2026-02-15 | 2026-02-10 | Closed |  |  | Supplier provided replacement material with acceptable finish.
NCR-2026-002 | 2026-02-03 | Manufacturing | Emily Johnson | Houston | Production | Valve Assembly Line | Torque readings on final assembly station were below documented work instruction range. | WI-220 Final Assembly Torque Requirements | Critical | 45 | 12600 | Stopped line, segregated product, and rechecked torque settings. | Equipment | Calibrate torque controller and retrain operators. | Add weekly torque verification to layered process audit. | David Brown | 2026-03-05 |  | Open |  |  | Affected units remain on quality hold pending disposition.
NCR-2026-003 | 2026-03-12 | Quality | Michael Davis | Phoenix | Documentation | Inspection Records | Final inspection records were missing required lot traceability fields. | ISO 9001:2015 Clause 7.5 Documented Information | Major | 78 | 3100 | Placed related shipment records on hold and opened document review. | Documentation | Revise inspection form to require lot number entry before approval. | Conduct monthly record completeness audits. | Ashley Wilson | 2026-10-01 |  | In Progress |  |  | Form revision is under quality review.
NCR-2026-004 | 2026-04-05 | Warehouse | Ashley Wilson | Dallas | Shipping | Packaged Control Panels | Control panel cartons were crushed during outbound handling and failed visual inspection. | WI-315 Packaging and Shipping Standards | Major | 16 | 2250 | Held damaged cartons and inspected all related pallets. | Process | Replace damaged packaging and revise pallet stacking instruction. | Add dock handling observation to weekly warehouse review. | Chris Anderson | 2026-05-06 | 2026-05-02 | Closed |  |  | No additional shipping damage found after revised stacking method.
NCR-2026-005 | 2026-05-18 | Quality | David Brown | Austin | Inspection | Pressure Test Station | Pressure test fixture allowed a reading outside the approved measurement tolerance. | CAL-108 Measurement System Control Procedure | Critical | 32 | 7400 | Removed fixture from service and retested prior inspections. | Equipment | Replace worn fixture seal and complete measurement system analysis. | Schedule quarterly fixture maintenance and calibration checks. | Jessica Martinez | 2026-08-30 |  | Pending Verification |  |  | Verification testing is scheduled after maintenance completion.
NCR-2026-006 | 2026-06-25 | Customer Service | Jessica Martinez | Seattle | Customer Complaint | Smart Thermostat | Customer reported intermittent display failures after installation at three sites. | Product Specification PS-410 Display Performance | Major | 9 | 5850 | Opened service cases and provided replacement units to affected customers. | Material | Analyze returned units and replace suspect display component lot. | Expand incoming inspection sampling for display modules. | Sarah Taylor | 2026-09-20 |  | Open |  |  | Returned units are awaiting engineering failure analysis.
NCR-2026-007 | 2026-07-10 | Manufacturing | Chris Anderson | Los Angeles | Production | Printed Circuit Board Assembly | Solder bridges were detected on multiple boards during automated optical inspection. | IPC-A-610 Class 2 Acceptance Requirements | Major | 64 | 6900 | Stopped affected work order and segregated boards for reinspection. | Training | Retrain operators on solder paste application and revise setup checklist. | Perform monthly competency checks for soldering operators. | Robert Thomas | 2026-08-25 |  | In Progress |  |  | Operator training completed; process validation remains open.
NCR-2026-008 | 2026-08-03 | Supply Chain | Sarah Taylor | New York | Supplier | Stainless Steel Fasteners | Supplier shipment included mixed fastener grades within a single labeled container. | PO-558 Material Identification Requirements | Minor | 400 | 1800 | Quarantined container and completed sort of all fasteners. | Supplier | Require supplier to submit improved labeling and segregation plan. | Add supplier packaging verification to receiving inspection. | Amanda Moore | 2026-09-06 | 2026-09-02 | Closed |  |  | Replacement shipment received with correct grade segregation.
NCR-2026-009 | 2026-08-22 | Quality | Robert Thomas | Philadelphia | Inspection | Calibration Certificates | Calibration certificate review found an expired reference standard used during inspection. | CAL-102 Calibration Control Procedure | Critical | 22 | 9200 | Suspended certificate release and reviewed all impacted measurements. | Documentation | Recalibrate reference standard and reassess impacted inspection results. | Implement automated expiration alert before certificate release. | James Miller | 2026-09-15 |  | Pending Verification |  |  | Impact assessment is in progress with metrology support.
NCR-2026-010 | 2026-09-01 | Engineering | Amanda Moore | San Antonio | Documentation | Installation Manual | Installation manual omitted the required grounding verification step. | ENG-501 Product Documentation Standard | Major | 150 | 3400 | Stopped distribution of current manual and issued temporary field notice. | Human Error | Update manual, complete technical review, and release controlled revision. | Use document change checklist with independent peer review. | Emily Johnson | 2026-10-15 |  | Open |  |  | Controlled revision is being drafted by engineering.
Total Estimated Cost Impact
Formulas:
Days Open = IF([Date Reported]="","",IF([Actual Closure Date]="",TODAY()-[Date Reported],[Actual Closure Date]-[Date Reported]))
Overdue Flag = IF([Date Reported]="","",IF([Target Due Date]="","",IF(AND([Status]<>"Closed",[Target Due Date]<TODAY()),"Overdue","On Track")))

## NCR Dashboard
Non-Conformance Report Dashboard
Total NCRs |  | Open NCRs |  | Closed NCRs | [5 empty] | NCR Lookup
[10 empty] | NCR ID | NCR-2026-001
Overdue NCRs |  | Total Cost Impact |  | Closure Rate | [5 empty] | Current Status
Average Days Open
NCRs by Status |  | NCRs by Severity |  | NCRs by Department |  | NCRs by Root Cause Category |  | Cost Impact by Department
Status | NCR Count | Severity | NCR Count | Department | NCR Count | Root Cause Category | NCR Count | Department | Cost Impact
Open |  | Critical |  | Manufacturing |  | Supplier |  | Manufacturing
In Progress |  | Major |  | Quality |  | Process |  | Quality
Pending Verification |  | Minor |  | Supply Chain |  | Training |  | Supply Chain
Closed |  |  |  | Warehouse |  | Documentation |  | Warehouse
|  |  |  | Customer Service |  | Equipment |  | Customer Service
|  |  |  | Engineering |  | Material |  | Engineering
Human Error
Customer Requirement

## Instructions
Non-Conformance Report Workbook Instructions
Step | Guidance
1 | Enter each issue as a separate NCR record in the Non-Conformance Log.
2 | Assign a unique NCR ID, such as NCR-2026-001, before documenting the issue.
3 | Record the objective requirement, procedure, specification, or standard that was not met.
4 | Document the immediate containment action before selecting corrective and preventive actions.
5 | Assign one responsible owner and enter a practical target due date for the corrective action.
6 | Update the status, actual closure date, verification result, and final disposition after implementation.
7 | Review records marked Overdue weekly and update the action plan or due date when necessary.
8 | Use the NCR Dashboard to monitor trends, closure rate, severity, department workload, and financial impact.
Legend | Meaning
Input cells | Pale yellow cells are editable data-entry fields.
Formula cells | Calculated fields such as Days Open and Overdue Flag update automatically.
Closed status | Green indicates a completed NCR with final status Closed.
Overdue or Critical | Red indicates an overdue action or Critical severity requiring attention.
Open or In Progress | Amber indicates an active record requiring follow-up.
Severity levels | Critical: serious risk or major impact. Major: meaningful process or product impact. Minor: limited impact.
Recommended review | Review open and overdue NCRs weekly. Review trends and cost impact with management monthly.