## Project Plan
Task ID | Task Name | Project Phase | Milestone | Owner | Department | City | Start Date | Due Date | Status | Priority | Completion % | Planned Hours | Actual Hours | Budget | Actual Cost | Variance | Days Remaining | On Track? | Notes | Lookup Phase | Reference Milestone | Reference Phase
P-001 | Requirements Workshop | Planning | Requirements Approved | Emily Carter | Product | New York | 2026-01-12 | 2026-02-06 | Complete | High | 100% | 24 | 26 | 4800 | 5100 |  |  |  | Stakeholder requirements approved. |  | Requirements Approved | Planning
P-002 | Project Charter | Planning | Charter Signed | James Wilson | PMO | Chicago | 2026-01-19 | 2026-02-13 | Complete | High | 100% | 20 | 18 | 3500 | 3200 |  |  |  | Executive sponsor signed the charter. |  | Charter Signed | Planning
P-003 | UX Wireframes | Design | Design Review Complete | Ashley Martinez | Design | Austin | 2026-03-02 | 2026-03-27 | Complete | Medium | 100% | 48 | 46 | 6800 | 6500 |  |  |  | Reviewed wireframes incorporated into the design system. |  | Design Review Complete | Design
P-004 | Technical Architecture | Design | Architecture Approved | Michael Brown | Engineering | Seattle | 2026-04-06 | 2026-05-08 | Complete | High | 100% | 72 | 76 | 12000 | 13000 |  |  |  | Architecture decision record approved. |  | Architecture Approved | Design
P-005 | Database Setup | Development | Database Ready | David Johnson | Engineering | Dallas | 2026-05-18 | 2026-06-19 | Complete | High | 100% | 56 | 54 | 8500 | 8100 |  |  |  | Production database environment is ready. |  | Database Ready | Development
P-006 | API Development | Development | API Beta Complete | Chris Davis | Engineering | Houston | 2026-06-15 | 2026-07-31 | In Progress | High | 65% | 140 | 128 | 18000 | 16600 |  |  |  | Two endpoint groups remain under integration testing. |  | API Beta Complete | Development
P-007 | User Acceptance Testing | Testing | UAT Sign-Off | Jessica Miller | QA | Los Angeles | 2026-08-03 | 2026-09-18 | In Progress | High | 80% | 96 | 74 | 11000 | 7600 |  |  |  | Business testers are validating final workflows. |  | UAT Sign-Off | Testing
P-008 | Training Materials | Launch | Training Complete | Sarah Anderson | Operations | Phoenix | 2026-08-24 | 2026-10-02 | In Progress | Medium | 45% | 44 | 21 | 5400 | 2100 |  |  |  | Draft facilitator guide is in review. |  | Training Complete | Launch
P-009 | Production Deployment | Launch | Go-Live | Robert Taylor | IT | San Antonio | 2026-09-21 | 2026-10-16 | Not Started | High | 0% | 80 | 0 | 15000 | 0 |  |  |  | Deployment window is reserved with infrastructure operations. |  | Go-Live | Launch
P-010 | Project Closeout | Closeout | Lessons Learned Complete | Amanda Thomas | PMO | Philadelphia | 2026-10-05 | 2026-10-30 | Not Started | Low | 0% | 32 | 0 | 4000 | 0 |  |  |  | Closeout meeting will follow production stabilization. |  | Lessons Learned Complete | Closeout
Formulas:
Days Remaining = IF(OR([Task ID]="",[Due Date]=""),"",IF([Status]="Complete",0,[Due Date]-TODAY()))

## Dashboard
Project Plan Dashboard
Project KPI | Value |  | Status Summary | Task Count
Total Tasks |  |  | Not Started
Completed Tasks |  |  | In Progress
Overall Completion |  |  | Complete
Total Budget |  |  | On Hold
Actual Cost
Budget Variance |  |  | Project Phase | Task Count | Average Completion | Total Budget | Actual Cost
At-Risk Tasks |  |  | Planning
Average Planned Hours |  |  | Design
Development
Testing
Launch
Closeout
Sequence | Milestone | Owner | Due Date | Status

## Instructions
Project Plan With Milestones Template Guide
Guide Topic | How to Use This Workbook
Project Plan | Enter one task per row on the Project Plan sheet. Add new tasks in the prepared rows below the sample tasks and keep each Task ID unique.
Task Details | Update Task Name, Project Phase, Milestone, Owner, Department, City, Start Date, Due Date, and Notes as the project changes.
Status and Priority | Use the Status dropdown to select Not Started, In Progress, Complete, or On Hold. Use the Priority dropdown to identify High, Medium, or Low priority work.
Completion % | Enter Completion % as a percentage from 0% to 100%. The On Track? result uses the completion percentage together with the due date.
Milestones | Milestone names and due dates feed the Dashboard timeline. The Lookup Phase helper uses a milestone reference lookup to confirm the expected project phase.
Budget Tracking | Budget is the planned amount. Actual Cost is the amount spent. Variance is calculated as Actual Cost minus Budget, so a negative value indicates spending below budget.
Project Health | Complete means the task is finished. On Track means the task is at least 75% complete and not overdue. Monitor means the task needs attention. At Risk means the due date has passed before completion.
Days Remaining | Days Remaining updates automatically with TODAY(). Completed tasks show zero days remaining.
Dashboard | Use the Dashboard for project KPIs, status counts, phase-level budget comparisons, and the milestone due-date trend.
Formula Cells | Pale yellow cells are intended for editing. Formula-driven fields such as Variance, Days Remaining, On Track?, KPI values, and dashboard summaries update automatically.