## Budget Detail
Cost Code | Budget Category | Subcategory | Description | Vendor | Invoice # | Budgeted Amount | Actual Amount | Variance | Variance % | Status | Due Date | Paid Date | Notes
01-100 | Sitework | Excavation | Lot clearing and excavation for foundation | James Miller Excavating - Dallas, TX | INV-1001 | 18000 | 18500 |  |  |  | 2026-02-15 | 2026-02-20 | Extra rock removal added cost
02-200 | Foundation | Concrete | Foundation walls and footings pour | Miller Concrete Co - Phoenix, AZ | INV-1002 | 42000 | 41200 |  |  |  | 2026-03-10 | 2026-03-12 | Came in under budget
03-300 | Framing | Lumber | Framing lumber package delivery | Atlanta Building Supply - Atlanta, GA | INV-1003 | 65000 | 67300 |  |  |  | 2026-04-05 | 2026-04-10 | Lumber price increase mid-project
04-400 | Roofing | Labor & Materials | Shingle roof install, labor and materials | Charlotte Roofing Co - Charlotte, NC | INV-1004 | 21000 | 20500 |  |  |  | 2026-05-01 | 2026-05-03 | On schedule
05-500 | Plumbing | Rough-In | Plumbing rough-in including permit fees | Denver Plumbing Pros - Denver, CO | INV-1005 | 15500 | 16200 |  |  |  | 2026-05-15 |  | Permit fee higher than estimated
06-600 | Electrical | Rough-In | Electrical rough-in wiring, subcontractor labor | Robert Taylor Electrical - Dallas, TX |  | 17800 | 0 |  |  |  | 2026-06-01 |  | Awaiting invoice from subcontractor
07-700 | HVAC | System Install | HVAC system installation, full house | Wilson HVAC Solutions - Phoenix, AZ | INV-1007 | 23000 | 23000 |  |  |  | 2026-06-15 | 2026-06-18 | Exact budget match
08-800 | Insulation/Drywall | Install | Insulation and drywall package | Davis Drywall & Insulation - Atlanta, GA | INV-1008 | 19500 | 0 |  |  |  | 2026-07-01 |  | Invoice pending final inspection
09-900 | Interior Finishes | Trim & Doors | Interior trim and door installation | Ashley Brown Millwork - Charlotte, NC | INV-1009 | 28000 | 27100 |  |  |  | 2026-08-01 | 2026-08-05 | Minor change order savings
10-950 | Interior Finishes | Flooring | Flooring and finish materials | Emily Johnson Flooring Co - Denver, CO | INV-1010 | 24000 | 25600 |  |  |  | 2026-08-20 | 2026-08-25 | Upgraded hardwood in kitchen

## Budget Summary
Residential Construction Budget Summary
Total Budget | Total Actual | Total Variance | Overall Variance % | Open Items
Budget Category | Total Budgeted | Total Actual | Total Variance | Variance % | % of Total Budget
Sitework
Foundation
Framing
Roofing
Plumbing
Electrical
HVAC
Insulation/Drywall
Interior Finishes
Landscaping/Final Cleanup
TOTAL

## Dashboard
Construction Budget Dashboard
Total Budget | Total Actual | Variance | Over Budget Items | On Budget Items
Top 5 Over-Budget Items
Description | Vendor | Budgeted | Actual | Variance
Cumulative Planned vs Actual Spend
Line Item | Cumulative Budgeted | Cumulative Actual

## Instructions
How to Use This Residential Construction Budget Template
Budget Detail Sheet | Enter each cost line item with its Cost Code, Budget Category, Subcategory, Description, Vendor, and Invoice #. Enter the Budgeted Amount when the estimate is finalized, and the Actual Amount once an invoice is received. Variance, Variance %, and Status calculate automatically.
Status Meaning | "Pending" means no actual amount has been entered yet. "On Budget" means the actual amount is at or below the budgeted amount. "Over Budget" means the actual amount exceeds the budgeted amount. These update automatically from the formulas in column K.
Vendor, Invoice, and Payment Dates | Update the Vendor and Invoice # columns as bids and invoices are received. Enter the Due Date when payment is expected and the Paid Date once payment has been made. Leave Paid Date blank for unpaid items.
Color Coding | Positive variance (actual higher than budget) is highlighted in green, negative variance (actual lower than budget) is highlighted in red, and pending items with no actual amount are highlighted in amber. Pale yellow cells are meant for manual data entry.
Budget Summary Sheet | This sheet automatically rolls up totals by Budget Category using SUMIF formulas that pull from the Budget Detail sheet. Key performance indicators at the top show Total Budget, Total Actual, Total Variance, Overall Variance %, and the number of Open (Pending) Items.
Dashboard Sheet | Provides a visual snapshot with KPI tiles, a Budget vs Actual bar chart by category, a cumulative spend line chart, a budget share pie chart, and a table of the Top 5 Over-Budget line items ranked automatically by variance.
Data Entry Notes | Enter all costs in US dollars (USD). Use standard US date format MM/DD/YYYY for all Due Date and Paid Date entries. Avoid deleting formula cells in columns I, J, and K on the Budget Detail sheet, as the Summary and Dashboard sheets depend on them.
Adding New Line Items | To add a new cost line, insert a new row within the Budget Detail table, fill in all columns, and copy the formulas from columns I, J, and K down into the new row. Then extend the ranges referenced by the Budget Summary and Dashboard formulas if needed.